## RFI Log
No. | Subject | Status | Ball in court | Raised by | Sent to | Priority | Date issued | Response due | Date answered | Days open | Cost impact | Schedule impact | Sheet | Rev | Answer (verbatim)
001 | SAMPLE: Beam depth at grid C4 conflicts with duct main | Answered | GC to close | M. Alvarez, Supt | R. Chen, Struct. Eng. | High | 2026-07-06 | 2026-07-13 | 2026-07-10 |  | Yes | No | S-201 | 2 | Drop bottom of beam to 9'-8" AFF per attached SK-12. Duct routes below. Issue SK-12 to field.
002 | SAMPLE: Door 114A hardware set not in spec 08 71 00 | Open | Architect | J. Okafor, PM | T. Marsh, Architect | Normal | 2026-07-21 | 2026-07-28 |  |  | TBD | No | A-601 | 1
003 | SAMPLE: Voided. Duplicate of 002 | Void |  | J. Okafor, PM |  | Low | 2026-07-22 |  |  |  | No | No | A-601 | 1 | Voided 2026-07-22. Row kept so the numbering holds.
004 | SAMPLE: Storefront head detail missing at column line 1 | Open | R. Chen, Struct. Eng. | M. Alvarez, Supt | R. Chen, Struct. Eng. | Normal | 2026-08-04 | 2026-08-11 |  |  | No | TBD | A-501 | 0
Formulas:
Days open = IF([Date issued]="","",IF([Date answered]="",TODAY()-[Date issued],[Date answered]-[Date issued]))

## How to keep it
The RFI log, kept right
From Oriel (oriel.build). Free to use and share. The four sample rows in the log are fictional. Delete them before you start.
FIVE RULES
1. Number once, never reuse. | A dead RFI gets voided, and its row stays. Renumbering breaks every reference to the log that anyone has already made.
2. Date every handoff. | The log's job is to say whose court each question sits in and since when. An undated handoff is a rumor.
3. Answers verbatim. | Paste what they wrote, word for word, in the Answer column. A paraphrase is your claim. A quote is their answer.
4. Nothing gets deleted. | Wrong entry? Add a correcting row and mark the old one Void. A log with eraser marks loses the argument it exists to win.
5. One log, where everyone reads it. | The moment answers live in two places, you are back to the inbox.
THE COLUMNS
No. | Sequential, assigned once. 001, 002, 003. Never reused, never reissued.
Subject | One line, specific enough that someone can find this row in a year.
Status | Draft, Open, Answered, Closed, or Void. Answered means a response is in; Closed means the field is done with it.
Ball in court | Who owes the next move, by name or company. The most-read column in the log.
Raised by | Who asked. Name and role.
Sent to | Who was asked. Name and firm.
Priority | High, Normal, or Low. High means work is waiting on the answer.
Date issued | The day the question left your desk, not the day you wrote it.
Response due | The day an answer is owed. Contracts often set this; 7 calendar days is a common default.
Date answered | The day the written answer arrived. Filled in, it stops the Days open counter.
Days open | Counts itself. Today minus issued until answered, then fixed.
Cost impact | Yes, No, or TBD. Flag it early; the estimate comes later.
Schedule impact | Yes, No, or TBD.
Sheet | The drawing sheet the question is about. S-201, A-601.
Rev | The revision of that sheet you were looking at when you asked. Answers age; this pins what they answered against.
Answer (verbatim) | Their words, pasted. Attach or reference any sketch they issued.
A row turns red when its response is overdue: past due date, no answer, not closed or void.
Oriel keeps this log itself: every question pinned to the drawing it is about, answered through a link, filed in a record that cannot be quietly edited. oriel.build